**Election Timeline 2021**

Date **Election** Activity

**02/01/21 Call for nominations**

**02/14/21 Nominations end (open 14 days)**

02/15/21 Admin starts; grace period starts

02/17/21 Grace period ends (3 days)

02/24/21 Admin work ends-ballot done (10 days)

**02/25/21 Voting begins**

**03/17/21 Voting ends (Open 21 days)**

03/18/21 Tabulating starts

03/19/21 Tabulating ends (2 days)

**03/20/21 Notification begins**

Chair notifies Secretary

 Secretary notifies board, candidate, members

 \*Appeals process begins- ends 7 days after notification of results

**03/23/21 Notification ends (3 days)**

Date **Election Tie** Activity

03/19/21 Tabulation Ends for Regular Vote- Tie admin starts

03/20/21 Tie Admin ends (ballot complete)

**03/21/21 Tie Voting begins (3 days from discovery of tie)**

**03/25/21 Tie Voting ends (Open 5 days)**

03/26/21 Tie Tabulating begins

03/27/21 Tie Tabulating ends (2 days)

03/28/21 Tied Notification begins

\*Appeals process begins- ends 7 days after notification of results